## Home - Overview
Implementation Project Workbook | [9 empty] | 2023-12-15
|  | PROJECT DETAILS | QUALITY METRICS | BUDGET METRICS | WEEKLY NOTES | CHANGE LOG | HOME
Useful Resources
JIRA
Timetracking Platform
Schedule Deviation
0%
-0.8925%
0%
-1.338%
-0.223%
0.4459%
0.2229%
[10 empty] | -1.785% | Total
Calculation
|  |  |  | Category | Estimated | Actual | ETC (Est. Time to Complete | Total Forecasted | EV (Est. Variance)
|  |  |  | Billable - Baseline Hours | 0 | 0 | 0 | 0 | 0
|  |  |  | Non - Billable - Baseline Hours | 0 | 0 | 0 | 0 | 0
|  |  |  | Change Management Hours | 0 | 0 |  | 0 | 0
|  |  |  | Non - Billable Change Management Hours | 0
|  |  |  | Maintenance Hours |  | 0
|  |  |  | Total | 0 | 0 | 0 | 0 | 0
Change Request Break Down
|  | Submitted | 1
|  | On - Hold | 2
|  | Cancelled | 3
|  | Approved | 4
|  | In Development | 5
|  | Code Complete | 6
|  | Code Delivered | 7
|  | Customer Tested | 8
|  | CR Complete | 9
Weekly Updates / Notes: |  |  |  | Change Request Log
Topic: | Details | Update/Follow Up Date | Owner | Change Request Title | CR # | Status | Logged Date | Approval Date (If Applicable) | CR Total (Hours) | Total Cost | Business Estimate | Dev Estimate
Code Drop - Release #1 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 1 | 1 | Submitted | 2023-11-25 |  | 5.2 | 910 | 4 | 5
Code Drop - Release #2 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 2 | 2 | On - Hold | 2023-11-27 |  | 27.1 | 4065 | 9 | 20
Code Drop - Release #3 | Code Drop - Release #3 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 3 | 3 | On - Hold | 2023-11-29 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #4 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 11 | 11 | In Development | 2023-12-15 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #5 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 12 | 12 | In Development | 2023-12-17 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #6 | Code Drop - Release #3 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 13 | 13 | In Development | 2023-12-19 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #7 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 14 | 14 | In Development | 2023-12-21 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #8 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 15 | 15 | In Development | 2023-12-23 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #9 | Code Drop - Release #3 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 29 | 29 | Customer Tested | 2024-01-20 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #10 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 30 | 30 | Customer Tested | 2024-01-22 |  | 18.3 | 2745 | 9 | 15
Code Drop - Release #11 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher | Test 31 | 31 | Customer Tested | 2024-01-24 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 32 | 32 | Customer Tested | 2024-01-26 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 33 | 33 | Customer Tested | 2024-01-28 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 34 | 34 | Customer Tested | 2024-01-30 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 35 | 35 | Customer Tested | 2024-02-01 |  | -6.34 | -951 | 9 | 1
|  |  |  | Test 36 | 36 | Customer Tested | 2024-02-03 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 37 | 37 | CR Complete | 2024-02-05 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 38 | 38 | CR Complete | 2024-02-07 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 39 | 39 | CR Complete | 2024-02-09 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 40 | 40 | CR Complete | 2024-02-11 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 41 | 41 | CR Complete | 2024-02-13 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 42 | 42 | CR Complete | 2024-02-15 |  | -6.34 | -951 | 9 | 1
|  |  |  | Test 43 | 43 | CR Complete | 2024-02-17 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 44 | 44 | CR Complete | 2024-02-19 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 45 | 45 | CR Complete | 2024-02-21 |  | 18.3 | 2745 | 9 | 15
|  |  |  | Test 22 | 22 | Code Delivered | 2024-01-06 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 23 | 23 | Code Delivered | 2024-01-08 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 24 | 24 | Code Delivered | 2024-01-10 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 25 | 25 | Code Delivered | 2024-01-12 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 26 | 26 | Code Delivered | 2024-01-14 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 27 | 27 | Code Delivered | 2024-01-16 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 28 | 28 | Code Delivered | 2024-01-18 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 16 | 16 | Code Complete | 2023-12-25 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 17 | 17 | Code Complete | 2023-12-27 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 18 | 18 | Code Complete | 2023-12-29 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 19 | 19 | Code Complete | 2023-12-31 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 20 | 20 | Code Complete | 2024-01-02 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 21 | 21 | Code Complete | 2024-01-04 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 4 | 4 | Cancelled | 2023-12-01 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 5 | 5 | Cancelled | 2023-12-03 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 6 | 6 | Cancelled | 2023-12-05 |  | 4.22 | 633 | 9 | 7
|  |  |  | Test 7 | 7 | Approved | 2023-12-07 |  | 19.2 | 2880 | 8 | 15
|  |  |  | Test 8 | 8 | Approved | 2023-12-09 |  | 19.2 | 2880 | 8 | 15
|  |  |  | Test 9 | 9 | Approved | 2023-12-11 |  | 19.2 | 2880 | 8 | 15
210
Contractual Hours
$36,750
Project Cost ($)
Apple Implementation
Project Type
Internal Team
(1.78)%▼
Schedule Deviation
12/15/2023
Today's Date
Darius Crrutcher
Teammate #1
Teammate #2
External Team
External Member #1
External Member #2
External Member #3
Teammate #3
External Member #4
Navigation Tabs
Early-Stage
Mid-Stage
Late-Stage
484.98
Approved Change Request Hours
31.58
Current Defect Average:
484.98
Approved CR Hours

## Project Details
Implementation Project Workbook
|  | PROJECT DETAILS | QUALITY METRICS | BUDGET METRICS | WEEKLY NOTES | CHANGE LOG | HOME
Useful Resources
Project Details | [6 empty] | JIRA
Timetracking Platform
Project Details | Thomasville National Bank | Internal Project Team | External Project Team | Communciation Cadence |  | Frequency
Line of Business | Apple Implementation | Darius Crrutcher | External Member #1 | Weekly Internal Calls Set Up |  | Weekly
Contracted Hours | 210 | Teammate #1 | External Member #2 | Weekly External Calls Set Up |  | Weekly
$ Rate | 175 | Teammate #2 | External Member #3
Overall Expected Cost | 36750 | Teammate #3 | External Member #4
Agreement Signing Date | 2022-08-19 | 44806 | Tells me the dimensions of the graph for timeframing.
Original Start Date | 2022-09-02 | 44892
Projected Finish Date | 2022-11-27
|  |  | Dates & Duration - Inputs |  | Calculation
Major Deliverables/Accomplishments | Start | Orginal - End | Actual - End | Duration | Schedule Deviation
Delivery of Statement of Work | 2022-09-02 | 2022-09-04 | 2022-09-04 | 2 | 0%
Statement of Work Signed & Approved | 2022-09-04 | 2022-09-14 | 2022-09-18 | 10 | -0.8925%
Project Kick-Off Call | 2022-09-14 | 2022-09-24 | 2022-09-24 | 10 | 0%
Disocvery Phase Initation | 2022-09-24 | 2022-10-14 | 2022-10-20 | 20 | -1.338%
Architecture Doc. Delivered | 2022-10-14 | 2022-10-19 | 2022-10-20 | 5 | -0.223%
Environment Setup | 2022-10-19 | 2022-10-24 | 2022-10-22 | 5 | 0.4459%
Adaptation Phase Initation | 2022-10-24 | 2022-10-29 | 2022-10-28 | 5 | 0.2229%
UAT Code Drop | 2022-10-29 | 2022-11-05 |  | 7
Production Environment Installation | 2022-11-05 | 2022-11-12 |  | 7
Deployment Phase (Pilot) | 2022-11-12 | 2022-11-17 |  | 5
Deployment Phase | 2022-11-17 | 2022-11-22 |  | 5
Operational Transition | 2022-11-22 | 2022-11-27 |  | 5
|  |  |  | 86 | -1.785% | Total(s)
Formulas:
Thomasville National Bank = [PROJECT DETAILS, row above]
PROJECT DETAILS = [Thomasville National Bank]+[BUDGET METRICS]
Navigation Tabs
Navigation Tabs
Today's Date

## Quality Metrics
Implementation Project Workbook
|  | PROJECT DETAILS | QUALITY METRICS | BUDGET METRICS | WEEKLY NOTES | CHANGE LOG | HOME
Useful Resources
Dev Hours (Timetracking Platform) | 2160 | [5 empty] | JIRA
Function Points (Dev Hours / 67.5) | 32 | [5 empty] | Timetracking Platform
| Defect Count |  | Defect Break Down |  | Overall Issue Tracker
ARGO (JIRA) | 180 | JIRA | New | 15 | CNR | 9
Defects Blocked | 2 | Issue Tracker | In Development | 8 | WAD | 7
Defect Updated Information | 1 |  | Hold On / Blocked | 2 | Enhancement | 5
Defects Open/In Progress | 30 |  | In QA | 2 | Defects | 30
Total Defects Created | 43 |  | Ready for Release | 3
Closed Defects | 17 |  | Client Release | 4
Closed Overall Items | 46 |  | Closed | 17
Quality Metrics
Overall Defect Rate |  |  | Overall Standard |  |  | Testing Efficiency |  |  | Overall Standard
Stakeholders | Internal | Client | Green | Yellow | Red | Stakeholders | Internal | Client | Green | Yellow | Red
Calculation | 0.18 | 1.07 | < 4.5 : 1 | > 4.5 : 1 AND <= 6.5 | > 6.5 : 1 | Calculation |  | 0.09375 | > = 95% | > = 85% | < 85%
# of Function Points / # of Defects | [5 empty] | # of Function where Testing is Complete / Total # of Functions
Net Defect Trend |  |  | Early Stage |  |  | Defect First Time Resolution Rate (FTRR) |  |  | Early Stage
Stakeholders | Internal | Client | Green | Yellow | Red | Stakeholders | Internal | Client | Green | Yellow | Red
Calculation |  | 2.7059 | >= 1 AND <= 5 | > 5 AND <= 10 | > 10 | Calculation |  |  | >= 80% | >= 70% AND < 80% | < 70%
# of Defects Open During Period / # of Closed Issues in Period |  |  | Middle Stage |  |  | FTRR = # of Defects Resolved First Time / Total # of Defects Resolved |  |  | Late Stage
|  |  | Green | Yellow | Red |  |  |  | Green | Yellow | Red
|  |  | >= 1 AND <= 2 | > 2 AND < = 5 | > 5 |  |  |  | >= 90% | >= 80% AND < 90% | < 80%
|  |  | Middle Stage |  |  | User Acceptance Testing (UAT) Pass Rate
|  |  | Green | Yellow | Red | Stakeholders | Internal | Client | Green | Yellow | Red
|  |  | <= 1 | > 1 AND <= 2 | > 2 | Calculation
UAT Pass Rate = # of UAT Test Cases Passed / # of UAT Tests Cases Executed
Valid Defect Rate |  |  | Early Stage |  |  | UAT Test Execution Schedule Variance
Stakeholders | Internal | Client | Green | Yellow | Red | Stakeholders | Internal | Client | Green | Yellow | Red
Calculation |  | 36.96% | >= 80% | >= 70% AND < 80% | < 70% | Calculation
# of Defects Closed During Period / # of Closed Issues in Period |  |  | Late Stage |  |  | UAT Test Execution Schedule Variance = (# of UAT Test Cases Planned for Execution - # of UAT Test Cases Executed) / # of UAT Test Cases Executed
|  |  | Green | Yellow | Red
|  |  | >= 90% | >= 80% AND < 90% | < 80%
Defect Discovery Efficiency (Before) & (After Pilot) |  |  | BEFORE PILOT
Stakeholders | BEFORE | AFTER | Green | Yellow | Red
Calculation |  | 0 | > = 85% | > = 75% AND < 85% | < 75%
Total Expected Defects Prior to Pilot = Defects Discovered to Date / Testing Percent Complete |  |  | AFTER PILOT
Percent of Total Defects = Total Expected Defects Before Pilot / Total Expected Defects |  |  | Green | Yellow | Red
|  |  | < = 15% | > 15% AND <= 25% | > 25%
Defect Removal Efficiency |  |  | Overall Standard
Stakeholders | Internal | Client | Green | Yellow | Red
Calculation |  | 39.53% | > = 95% | > = 85% < 95% | < 85%
# of Defects Resolved / Total Defects
Defect Average
31.5833
Date Entered | Historical Defect Count | Expected Defects
2023-01-01 | 43 | 32 | 1st Day - Code Dropped Into Clients Environment
2023-01-07 | 43 | 32 | Add Lines Each Week following first code drop through remaining project life. | These date cells will utilize this formula "=IF(A53<>"",IF(B53="",NOW(),B53),"")"
2023-01-14 | 43 | 32
2023-01-21 | 40 | 32
2023-01-31 | 35 | 32
2023-02-05 | 35 | 32
2023-02-06 | 30 | 32
2023-02-16 | 30 | 32
2023-02-25 | 25 | 32
2023-03-14 | 20 | 32
2023-04-01 | 20 | 32
2023-04-10 | 15 | 32
2023-12-12 |  | 32 | Expected Completion Date of Project.
[5 empty] | 44927 | This lets me know how to formate my X-Axis for accuracy.
45272
Navigation Tabs
Navigation Tabs
Today's Date

## Budget Metrics
Implementation Project Workbook
|  | PROJECT DETAILS | QUALITY METRICS | BUDGET METRICS | WEEKLY NOTES | CHANGE LOG | HOME
Useful Resources
JIRA
Timetracking Platform
Budget Metrics
Forecasted | Calculation
| Forecasted Billable Hours | Forecasted Non -Billable Hours | Total Hours Forecasted Hours | Billable Difference: Forecasted vs. Revised Budget | Non - Billable Difference: Forecasted vs. Revised Budget | Total Difference: Forecasted vs. Revised Budget
Fixed | 0 | 0 | 0 | 0 | 0 | 0
Time & Materials (Change Requests) | 0 | 0 | 0 | 0 | 0 | 0
Maintenance | 0 | 0 | 0 | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0
Contingency Amount (10%) | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 0 | 0 | 0 | 0 | 0 | 0
Calculation
Completed | (Timetracking Platform) - Inputs
| Budgeted Billable Hours | Budgeted Non - Billable Hours | Total Budgeted Hours | Change Management Billable Hours | Change Management Non - Billable Hours | Revised Budget Billable Hours | Revised Budget Non - Billable Hours | Total Revised Budgeted Hours
Fixed |  |  | 0 |  |  | 0 | 0 | 0
Time & Materials |  |  | 0 |  |  | 0 | 0 | 0
Maintenance |  |  | 0 |  |  | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency Amount (10%) | 0 |  | 0 |  |  | 0 | 0 | 0
Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining | (Timetracking Platform) - Inputs |  |  | Calculation
| Actual Billable Hours | Actual Non - Billable | Actual Total Hours | Est. Billable Hours to Complete | Est. Non - Billable Hours to Complete
Fixed |  |  | 0 | 0 | 0
Time & Materials |  |  | 0 | 0 | 0
Maintenance |  |  | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0 | 0 | Calculation | Calculation
Contingency Amount (10%) |  |  | 0 |  |  | Remaining Hours | Contractual Hours
Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 210
Points
[7 empty] | Min | 0% | 0%
Estimation Chart Data Pull | Calculation | [5 empty] | Late Stage Hours | 25% | 2%
| Forecast | Budget | Variance |  |  |  | Mid-Stage Hours | 50% | 138%
Approved |  | 0 |  |  |  |  | Early Stage Hours | 25%
Change |  | 0 |  |  |  |  | Max | 100%
Used | 0
Remaining | 0
Variance |  |  | 0
Calculation
Category | Estimated | Actual | ETC (Est. Time to Complete | Total Forecasted | EV (Est. Variance)
Billable - Baseline Hours | 0 | 0 | 0 | 0 | 0
Non - Billable - Baseline Hours | 0 | 0 | 0 | 0 | 0
Change Management Hours | 0 | 0 |  | 0 | 0
Non - Billable Change Management Hours | 0
Maintenance Hours |  | 0
Total | 0 | 0 | 0 | 0 | 0
Navigation Tabs
Navigation Tabs
Today's Date

## Weekly Notes
Implementation Project Workbook
|  | PROJECT DETAILS | QUALITY METRICS | BUDGET METRICS | WEEKLY NOTES | CHANGE LOG | HOME
Useful Resources
Weekly Notes: | [6 empty] | JIRA
Timetracking Platform
Topic: | Details | Update/Follow Up Date | Owner
Code Drop - Release #1 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #2 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #3 | Code Drop - Release #3 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #4 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #5 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #6 | Code Drop - Release #3 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #7 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #8 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #9 | Code Drop - Release #3 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #10 | Code Drop - Release #1 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Code Drop - Release #11 | Code Drop - Release #2 is expected to drop by EOD x/xx/xx | x/xx/xx | Darius Crutcher
Navigation Tabs
Navigation Tabs
Today's Date

## Change Log
Implementation Project Workbook
|  | PROJECT DETAILS | QUALITY METRICS | BUDGET METRICS | WEEKLY NOTES | CHANGE LOG | HOME
[7 empty] | Useful Resources |  |  |  | Summary of Approved Hours & Cost
JIRA
[7 empty] | Timetracking Platform |  |  |  | 484.98 |  | 72747
[5 empty] | Calculation |  | Input |  | Calculation |  |  |  | Input
Change Request Title | CR # | Status | Logged Date | Approval Date (If Applicable) | CR Total (Hours) | Total Cost | Business Estimate | Dev Estimate | Anticipated # of Defects | Defect Fix | QA | PM | Hourly Rate ($175.00) | CR Status | #
Test 1 | 1 | Submitted | 2023-11-25 |  | 5.2 | 910 | 4 | 5 | 0.33333 | 2 | 1 | 1.2 | 175 | Submitted | 1
Test 2 | 2 | On - Hold | 2023-11-27 |  | 27.1 | 4065 | 9 | 20 | 1.3333 | 8 | 4 | 4.1 | 150 | On - Hold | 2
Test 3 | 3 | On - Hold | 2023-11-29 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Cancelled | 3
Test 11 | 11 | In Development | 2023-12-15 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Approved | 4
Test 12 | 12 | In Development | 2023-12-17 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | In Development | 5
Test 13 | 13 | In Development | 2023-12-19 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Code Complete | 6
Test 14 | 14 | In Development | 2023-12-21 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Code Delivered | 7
Test 15 | 15 | In Development | 2023-12-23 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Customer Tested | 8
Test 29 | 29 | Customer Tested | 2024-01-20 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | CR Complete | 9
Test 30 | 30 | Customer Tested | 2024-01-22 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150
Test 31 | 31 | Customer Tested | 2024-01-24 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Hours Approved |  | Associated Cost
Test 32 | 32 | Customer Tested | 2024-01-26 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150
Test 33 | 33 | Customer Tested | 2024-01-28 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Approved | 76.8 | 11520
Test 34 | 34 | Customer Tested | 2024-01-30 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | In Development | 91.5 | 13725
Test 35 | 35 | Customer Tested | 2024-02-01 |  | -6.34 | -951 | 9 | 1 | 0.066667 | 0.4 | 0.2 | 1.06 | 150 | Code Complete | 25.32 | 3798
Test 36 | 36 | Customer Tested | 2024-02-03 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Code Delivered | 29.54 | 4431
Test 37 | 37 | CR Complete | 2024-02-05 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Customer Tested | 121.76 | 18264
Test 38 | 38 | CR Complete | 2024-02-07 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | CR Complete | 140.06 | 21009
Test 39 | 39 | CR Complete | 2024-02-09 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150 | Total | 484.98 | 72747
Test 40 | 40 | CR Complete | 2024-02-11 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150
Test 41 | 41 | CR Complete | 2024-02-13 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150
Test 42 | 42 | CR Complete | 2024-02-15 |  | -6.34 | -951 | 9 | 1 | 0.066667 | 0.4 | 0.2 | 1.06 | 150
Test 43 | 43 | CR Complete | 2024-02-17 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150
Test 44 | 44 | CR Complete | 2024-02-19 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150
Test 45 | 45 | CR Complete | 2024-02-21 |  | 18.3 | 2745 | 9 | 15 | 1 | 6 | 3 | 3.3 | 150
Test 22 | 22 | Code Delivered | 2024-01-06 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 23 | 23 | Code Delivered | 2024-01-08 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 24 | 24 | Code Delivered | 2024-01-10 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 25 | 25 | Code Delivered | 2024-01-12 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 26 | 26 | Code Delivered | 2024-01-14 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 27 | 27 | Code Delivered | 2024-01-16 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 28 | 28 | Code Delivered | 2024-01-18 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 16 | 16 | Code Complete | 2023-12-25 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 17 | 17 | Code Complete | 2023-12-27 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 18 | 18 | Code Complete | 2023-12-29 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 19 | 19 | Code Complete | 2023-12-31 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 20 | 20 | Code Complete | 2024-01-02 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 21 | 21 | Code Complete | 2024-01-04 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 4 | 4 | Cancelled | 2023-12-01 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 5 | 5 | Cancelled | 2023-12-03 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 6 | 6 | Cancelled | 2023-12-05 |  | 4.22 | 633 | 9 | 7 | 0.46667 | 2.8 | 1.4 | 2.02 | 150
Test 7 | 7 | Approved | 2023-12-07 |  | 19.2 | 2880 | 8 | 15 | 1 | 6 | 3 | 3.2 | 150
Test 8 | 8 | Approved | 2023-12-09 |  | 19.2 | 2880 | 8 | 15 | 1 | 6 | 3 | 3.2 | 150
Test 9 | 9 | Approved | 2023-12-11 |  | 19.2 | 2880 | 8 | 15 | 1 | 6 | 3 | 3.2 | 150
Test 10 | 10 | Approved | 2023-12-13 |  | 19.2 | 2880 | 8 | 15 | 1 | 6 | 3 | 3.2 | 150
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0
Navigation Tabs
210
Contractual Hours
484.98
Approved CR Hours
Navigation Tabs
Today's Date